## PROJECT
COMMUNICATIONS MANAGEMENT PLAN
PROJECT DETAILS
PROJECT No: | MA-015-02
DATE: | 13/11/2021
FULL PROJECT NAME: | Sistem Informasi Senikersku
PROJECT MANAGER: | Gerald Elroy Van Ryan
PROJECT SPONSOR: | Bambang Suardi

## COMMUNICATIONS MANAGEMENT PLAN
COMMUNICATIONS MANAGEMENT PLAN
ID | STAKEHOLDER | INFORMATION | METHOD | TIMING OR FREQUENCY | SENDER | ASSUMPTIONS | CONSTRAINTS
S001 | Project Sponsor | Informasi mengenai update progress bulanan | Chat melalui whatsapp | 1 bulan sekali setiap minggu pertama | Project Manager / Communication Manager | - | Chat hanya dilakukan pada hari kerja, pukul 09:00-18:00
|  | Fitur, perubahan atau deliverables baru | Chat melalui whatsapp, Zoom Meeting bersama tim | Setiap key milestones tercapai, atau ada perubahan mendadak | Project Manager / Communication Manager | - | Sudah menginfokan adanya rapat maksimal 3 hari sebelum rapat dimulai
|  | Pengenalan tim & pengajuan project, serta menjelaskan kebutuhan fitur proyek | Chat melalui whatsapp, Zoom Meeting bersama tim | Satu kali saat panggilan | Project Manager | Asumsi bahwa Project Sponsor telah mengetahui topik pembahasan terlebih dahulu melalui Chat WhatsApp
S002 | Administrator | Pemberitahuan mengenai manual fitur baru, manual sistem informasi untuk disebarkan ke pengguna sistem | Email, chat melalui Whatsapp | Waktu TBA, tentatif | Project Manager / Communication Manager | Asumsi bahwa administrator belum mengetahui cara penggunaan dan fitur yang ada pada Sistem Informasi Senikersku | Ukuran file maksimum 25MB.
S003 | Customers | Pemberitahuan kepada pengguna akan adanya fitur baru, serta survey guna peningkatan pengalaman pengguna | Email dan pada website | Waktu TBA. | Project Manager | Asumsikan adanya metode pembayaran yang baru pada situs. Notifikasi akan diteruskan ke customer | Notifikasi diberikan hanya pada jam 09.00-20.00

## DEFINITIONS
DEFINITIONS
PROJECT MANAGER
The person with responsbility for managing and delivering the project. They will own this log, but may not be the person maintaining it.
PROJECT ID
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
PROJECT SPONSOR
The person with ultimate accountablity for the project. They will hold the purse strings.
PROJECT TITLE
The name of the project, this should align with the name given on other project documents (rather than being a nickname).
STAKEHOLDER ID
Give each stakeholder a unique identifier or reference so that it can be easily traced.
STAKEHOLDER
Enter the name of the stakeholder or stakeholder group.
INFORMATION
Give as much detail as you can about the information that the stakeholder/group needs to receive. For example, 'High level information on go live, new features and training dates. '
METHOD
Describe how the information will be communicated. For example, email, meetings, website updates, events etc.
TIMING OR FREQUENCY
Describe when and how often the information will be communicated. For some stakeholders a regular update may be needed for others it may be a one off tied to an event. For example, notification of a new system going online with key technical information for a network support team.
SENDER
Give the person who will be responsible for making sure the communication is sent. This might not necessarily be the person who writes the email or delivers a presentation, but will be the person who makes the arrangements.
ASSUMPTIONS
Include any assumptions that you have made about the communication. For example that new website pages will be available or that assets for the comms will be ready e.g. a new logo. It is worth noting any assumptions you have made about the comms being successfully recieved. For example, it might be that you are assuming all users have email access. You might also be assuming that spam filters will not be a problem. Or you may assume that all recipients can read English to a particular level.
CONSTRAINTS
Enter any factors that constrain the communication. For example, a date by which it must be delivered, or a max file size for email.
This template was provided by
https://www.stakeholdermap.com/

## CUSTOMISE
HOW TO CHANGE THE MENU ITEMS IN STATUS FIELDS
Default settings
We have not set any drop down menus, as it is likely that most projects will have different priorities and categories.
How to create a drop down menu
Click on Data tab > Data Validation > Settings > List
In the Source field enter the menu items separated by a comma.
To change the menu items
To change the menu options or remove the dropdown select Data > Data Validation > Settings > List
ADDITIONAL FIELDS YOU MIGHT WANT TO ADD
Actions - A column for any actions related to the communication or to manage an assumption.
Task ID/WBS ID - To record any associated tasks on the project schedule.
Risk ID - a look up to any associated risks.
Budget/costs estimate
Project ID - For large communications efforts you may have a separate project. For example there might be a project to translate comms into other languages.
Dependencies - Some comms may be dependent on other tasks being completed.
Approval/Sign-off - To record the person/group who has authority to approve the communication before it is sent.
This template was provided by
https://www.stakeholdermap.com/